## Summary
A.T.L.A.S. Review - Confirmation Workbook
Companion to docs/ATLAS_FRAMEWORK_REVIEW.md, baseline v0.1 (2026-09-18). Nothing has been executed; this is the sign-off sheet before Day 1.
How to use this workbook
1. Work through sheets 1 to 5 in order. Yellow cells are yours; every other cell is reference and should not be edited.
2. Use the dropdown in each response column. Cells colour green, amber, or red as you answer.
3. Where you choose 'Change' or 'Disagree', write the alternative in the next column so it can be folded back into the brief.
4. Sheet 4 (Verification) is filled during Day 1 as each phase gate runs, not now.
5. The Ref sheets carry the agreed maps (engines, cabinet, domains, task forces, integrations, voice, multimodal, governance, Day 1) for checking against.
6. Return the file, or paste the response columns back, and the brief is updated to v0.2.
Legend
Yellow fill | Cell for you to fill in
Green | Accepted / Yes / Pass
Amber | Need more information / Deferred / Not yet run
Red | Change / Disagree / Discuss / No / Fail
Progress (formulas update as you answer)
Sheet | Items | Answered | Positive | Hold | Negative | Remaining
1 Decisions | 14
2 Resolutions | 20
3 Risks | 18
4 Verification | 18
5 Checklist | 14
Total
Positive / Hold / Negative map to each sheet's dropdown: Decisions = Accept / Need more information / Change; Resolutions = Accept / - / Disagree; Risks = Yes / - / Discuss; Verification = Pass / Deferred / Fail; Checklist = Yes or N/A / - / No.
Example of a completed decision row (format only; not a real answer)
ID | Decision | Recommendation | Blocks | Your response | Your answer or alternative | Notes
D0 | Example: which mail client the node uses | Client A | Phase 2 | Change | Use client B, it already holds my accounts | Discussed 2026-09-19

## 1 Decisions
1 Decisions
Section 19. Yellow cells are yours. Choose a response, and if it is 'Change' write the alternative in column F.
ID | Decision | Recommendation | Blocks | Your response | Your answer or alternative | Notes
D1 | Inference backend: llama-server or Ollama | llama-server | Phase 2
D2 | Secure Boot: disable, or enrol keys for any DKMS module | Disable on a headless node behind a firewall | Phase 1
D3 | Where the LUKS recovery key and restic passphrase are kept off-node | Password manager plus a printed copy in a physical safe | Phase 1
D4 | Router model and embedding model | Qwen3.5 4B-class instruct, bge-m3 embeddings, bge-reranker-v2-m3 | Phase 2
D5 | Whether Bare-Metal OS Exploitation and Quantum Computing become domains | Hold in reserve until a concrete need | None
D6 | Sentinel feed list | CoinDesk, ASX and US index feed, RSS news, node telemetry | Sentinel enablement
D7 | Graph layer: Microsoft GraphRAG or LightRAG | LightRAG, lighter indexing on this hardware | Phase 2
D8 | The never-without-the-Principal list (16.3) | Adopt the ten proposed items | Phase 2
D9 | Retention rule for chats, logs, backups (10.4, 9.5) | Adopt proposed defaults | Phase 2
D10 | Primary vision engine: GLM-4.6V-Flash or Qwen2.5-VL | Test both in Phase 4, keep the better reader as primary, the other as cross-check | Phase 4
D11 | Apple .ipa build path | Principal's own Mac if one exists, otherwise a licensed cloud Mac runner, never OSX-KVM on this node | Phase 2 tool
D12 | Meditron-70B: include or skip | Include, optional, low priority | Phase 3
D13 | Vault idle auto-lock period | 15 minutes | Phase 2
D14 | Whether external directors get real mailboxes or aliases on the Workspace domain | Aliases on one Workspace mailbox per division, distinct display names and signatures | Phase 2

## 2 Resolutions
2 Resolutions
Section 18. Each row changes earlier text of the brief. 'Disagree' returns the item to the decision list.
ID | Contradiction or ambiguity found | Resolution adopted | Your response | Notes
C1 | Backend named as llama.cpp, then Ollama, then llama-server at different points | llama-server primary on Vulkan; Ollama optional. D1 confirms
C2 | Ubuntu 26.04 chosen, but Phase 4 needs ROCm PyTorch, which does not install cleanly on the 26.04 host | ROCm lives inside containers; host runs Vulkan only (3.4)
C3 | Windows 96 GB and Linux ~120 GB budgets both appeared | Linux numbers are binding (4.1)
C4 | KV-cache proposal mixed shipped features with unmerged research | Only shipped features adopted (4.3)
C5 | Meditron listed among PyTorch engines | Runs through llama.cpp (5.1)
C6 | Arthur's override bound to the abliterated engine "for legal dissection" | Override is Qwen3.5 (6.1)
C7 | Gideon and Minerva bound to the abliterated engine "for zero-hallucination" | Standard engine, retrieval-grounded (6.2)
C8 | Router described as an Open WebUI pipeline | Lives in the orchestrator; Filter is a relay (7.1)
C9 | Domain 27 phrased as "memetic warfare" and "sentiment manipulation" | Retained under Helena with phrasing softened to legitimate growth and attribution work
C10 | Domain profiles' "Stateless MRTR, dispatch and decouple" removes the approval gate | Isolated-context dispatch with tracked completion (8.6)
C11 | Sentinel described as a WSL2 cron job | systemd timer; there is no WSL (9.3)
C12 | Sentinel fed to Ren | Alaric and Silas under Arthur (9.3)
C13 | AEGIS described as a single zip | restic (9.5)
C14 | AEGIS destination on the same drive | Second drive plus optional external (9.5)
C15 | Celery framed as freeing "a background hardware thread" for a backtest that may call an LLM | CPU work decouples; GPU calls still serialise (9.7)
C16 | Estate memory inside the vault versus the vault as on-demand top-secret storage | Estate memory on the LUKS volume; vault content never persisted (10.5)
C17 | Four engine names that do not exist | Real replacements (15.3)
C18 | "Vector Cortex replaces chat logs" versus Open WebUI's own database | Supplements; retention rule under D9 (10.4)
C19 | Desktop recommended for a Linux novice, then Server chosen | Server with Cockpit (3.1)
C20 | Fish Audio requested, then excluded as non-local and research-licensed | Kokoro plus Chatterbox (14.1)

## 3 Risks
3 Risks
Section 20. Acknowledge each risk and its mitigation, or flag it for discussion.
ID | Risk | Likelihood | Impact | Mitigation | Acknowledged | Notes
R1 | PyTorch has no official gfx1151 wheel, the community wheel may break on update | High | High for Phase 4, none for the LLM layer | Pin versions, per-engine pass/fail, containerised so the host is untouched
R2 | Ollama's Vulkan path immature on 26.04 | Medium | High if chosen | D1: llama-server primary
R3 | ROCm 7.2.x does not install on the 26.04 host kernel | Certain | Medium | Never install ROCm on the host, containers only (3.4)
R4 | KV quantisation silently falls back to full precision on an unsupported architecture | Medium | High, unexpected OOM | V4 per-model check
R5 | A second engine loads before the first releases memory, node crashes | Medium without an arbiter | High | Engine Arbiter polls GPU memory before every load (4.2)
R6 | GraphRAG indexing is LLM-heavy and slow here | High | Medium | Idle-time Celery job on the resident small model, D7 LightRAG
R7 | Cloudflare token in a plain-text file | Certain today | High | Scoped token, mode 600, outside backups and repo (12.3)
R8 | Open WebUI phones home by default | Certain unless hardened | High for the zero-cloud rule | Offline hardening in Phase 2 (12.1)
R9 | RTL8127 10GbE driver missing on the 26.04 kernel | Low to medium | Medium | V1, fall back to the second port or a USB adapter
R10 | Sustained thermal load in a small chassis | Medium | Low | Monitor temperatures in Cockpit, the 130 W sustained rating is desktop-class
R11 | CGNAT prevents inbound WireGuard | Low, port forward already succeeded | High for remote access | V5 from mobile data, static IP from the ISP if needed
R12 | Fictitious directors corresponding as humans, AI non-disclosure | Medium | Medium to high, legal | Gideon's sensitive-tier check, approval gate, 16.5
R13 | Abliterated engine used for external output | Medium | Medium | Abliterated output always passes the same gate, never routine tier
R14 | Chatterbox continuation quirk in production speech | Medium | Low | V7 testing, Kokoro fallback per line
R15 | Prompt bloat from domain injection makes every dispatch slow | High without limits | High, usability | Three-card limit, compact cards, stable-prefix ordering (8.4, 4.4)
R16 | Backup passphrase or LUKS key lost with the node | Low | Catastrophic | D3, off-node storage, quarterly restore test
R17 | PyAnnote gated model not accepted, diarisation silently absent | Medium | Low | V6
R18 | Continuous vision enabled by drift rather than decision | Low | High, privacy | Separate capability flag under Alaric, logged, D8 item 7

## 4 Verification
4 Verification
Section 21. Filled in during Day 1 as each phase gate runs. Nothing is trusted until its row reads Pass.
ID | What Day 1 must prove | Where | Result | Evidence or notes
V1 | RTL8127 10GbE link up on the 26.04 kernel | Phase 1 pre-flight | Not yet run
V2 | fTPM present and enabled, TPM2 enrolment succeeds | Phase 1 step 2 | Not yet run
V3 | Kernel parameters accepted on 7.0, GPU reports the expected memory budget | Phase 1 post-reboot | Not yet run
V4 | Quantised KV cache actually applied per model, no silent fallback | Phase 3 step 2 | Not yet run
V5 | WireGuard reachable from mobile data via vpn.sovereign-node.link | Phase 1 step 7 | Not yet run
V6 | PyAnnote 3.1 gated model accepted and loading | Phase 2 step 5 | Not yet run
V7 | Voice casting listening test, Alaric and Gideon clones sourced | Phase 2 gate | Not yet run
V8 | PointLLM builds and runs on ROCm in the container | Phase 4 step 4 | Not yet run
V9 | Clay or Prithvi builds and runs | Phase 4 step 4 | Not yet run
V10 | All four core LLMs load, generate, swap, and release memory, measured tok/s within the expected bands | Phase 3 gate | Not yet run
V11 | Community PyTorch ROCm wheel passes tensor, matmul, and diffusion self-tests in the container | Phase 4 step 1 | Not yet run
V12 | Open WebUI makes no outbound connection after hardening (verified with the firewall log) | Phase 2 step 3 | Not yet run
V13 | restic backup completes and a restore verifies by checksum | Phase 2 step 7 | Not yet run
V14 | Engine Arbiter refuses a second large load while one is resident, and downgrades a Deep Think depth when the projected footprint exceeds budget | Phase 2 gate | Not yet run
V15 | Approval gate holds a standard-tier email until approved, routine-tier auto-sends and logs | Phase 2 gate | Not yet run
V16 | Router hard rule routes a "medical" message to Arthur even when the classifier disagrees, decision logged | Phase 2 gate | Not yet run
V17 | Sandbox memory cap kills a runaway process without affecting the node | Phase 2 gate | Not yet run
V18 | Vault opens by button, locks on idle, vault-tagged content absent from memory collections afterwards | Phase 2 gate | Not yet run

## 5 Checklist
5 Checklist
Section 22. Nothing runs until every row reads Yes or N/A.
# | Group | Item | Done | Notes
1 | Principal's actions | Answer D1 through D14, or accept the recommendations as written.
2 | Principal's actions | Relocate the Cloudflare token per 12.3 and delete CLOUDFLARE.txt.
3 | Principal's actions | Decide where the LUKS recovery key and restic passphrase will live off-node (D3).
4 | Principal's actions | Create the Google Cloud OAuth client for Gmail, Calendar, and Drive; be available for the one-time browser authorisations during Phase 2.
5 | Principal's actions | Confirm the Sentinel feed list (D6).
6 | Principal's actions | Confirm which mailboxes or aliases directors will send from (D14).
7 | Principal's actions | Source reference recordings for Alaric's and, if needed, Gideon's cloned voices.
8 | Principal's actions | Confirm whether a Mac exists for iOS builds (D11).
9 | Principal's actions | Have a monitor and keyboard available for Phase 1 only, in case first boot needs a hand.
10 | Build-side preconditions | Ubuntu 26.04 Server installed on the 4 TB drive; 8 TB drive unpartitioned.
11 | Build-side preconditions | BIOS: UMA minimum, IOMMU on, fTPM on, Secure Boot per D2.
12 | Build-side preconditions | LAN address reserved for the node on the router; UDP 51820 forward confirmed to that address.
13 | Build-side preconditions | Internet bandwidth known, so Phase 3 and 4 durations can be planned.
14 | Accepted resolutions | C1 through C20 in Section 18 are accepted; where the Principal disagrees, the item returns to the decision list.

## Ref Engines
Ref Engines
Sections 5.1, 6.1, 6.2. Engines, hemispheres, and the final persona-to-engine map.
Four core engines (one resident at a time)
Engine | Architecture | Disk, 4-bit | Decode | Role
gpt-oss-120b | 117B MoE, 5.1B active, MXFP4 | 63 GB | 30–55 tok/s | Default resident engine. Ren, Helena, Victor, Gideon, Minerva
gpt-oss-120b abliterated (Huihui, MXFP4 GGUF) | Same weights, refusals removed | 63 GB | Same | Valerie default; Ren on override
Nemotron 3 Super | 120B hybrid Mamba MoE, 12.7B active | 65–70 GB | ~18 tok/s | Arthur default. Silas, Alaric
Qwen3.5-122B-A10B | 122B MoE, 10B active, vision-capable, 256k context, multilingual | 65–70 GB | 18–19 tok/s | Override engine for long documents, images, drawings, future languages
The two hemispheres
| Ren Ackerman — Vanguard, Prime Director | Arthur Sterling — Architect, Estate Manager
Hemisphere | Offensive, creative, expansive, outward-facing | Defensive, regimented, private, guardian of personal data
Domain mandate | Corporate, Enterprise, Infrastructure, AEC | Estate, Private Health, Logistics, Family
Default engine | gpt-oss-120b | Nemotron 3 Super
Override engine | gpt-oss-120b abliterated, on Principal's order | Qwen3.5-122B-A10B for deep document reasoning
Sampling | High temperature (0.8) as Deep Think Generator | Low temperature, not zero, as Deep Think Adversary
Deep Think role | Generator: three divergent trajectories | Adversary: rubric-scored verdict, weak concepts killed
Code path | Writes sandbox code | Audits code for memory and safety before execution, as a second layer over the OS-level sandbox cap
Directors | Gideon, Silas, Valerie, Helena, Eleanor | Alaric, Minerva, Victor
Shadow Cabinet engine map
Director | Division | Remit | Default engine | Override | Speaks externally
Gideon Vance | Corporate | Legal & Compliance | gpt-oss-120b, high reasoning, retrieval-grounded | Qwen3.5-122B for long contracts | Yes, sensitive tier
Silas Thorne | Corporate | CFO: capital, audit, banking | Nemotron 3 Super + code interpreter for all arithmetic | none | Yes, standard tier
Valerie Cross | Corporate | Infrastructure, DevOps, AEC, cyber, AEGIS Sandbox | gpt-oss-120b abliterated | Qwen3.5-122B for drawings and images | Yes, standard tier
Helena Frost | Corporate | Communications, brand, PR, crisis | gpt-oss-120b | none | Yes, standard tier
Eleanor Croft | Corporate | Routing, scheduling, triage; the 4-Way Router's classifier | Resident 4B model | none | Yes, routine tier (scheduling)
Alaric Stone | Estate | Physical assets, security, threat mitigation; Sentinel threat watch | Nemotron 3 Super | none | Yes, sensitive tier
Minerva Hale | Estate | Private health, longevity; medical data | gpt-oss-120b, retrieval-grounded | Qwen3.5-122B for records and scans; Meditron-70B cross-check | Yes, sensitive tier
Victor Vale | Estate | Aviation, transport, concierge | gpt-oss-120b | none | Yes, routine tier

## Ref Domains
Ref Domains
Section 8.2. All thirty retained. Tier A loads freely, B on clear match, C on explicit match only.
Thirty domain knowledge profiles
# | Domain | Hemisphere | Owner | Tier
1 | Systems Architect & Cybersecurity | Corporate | Valerie | A
2 | Growth Executive (marketing, sales, PR, SEO) | Corporate | Helena | A
3 | Customer Success & Experience Lead | Corporate | Helena | B
4 | Data Scientist & AI Engineer | Corporate | Valerie | A
5 | CFO & Controller | Corporate | Silas | A
6 | General Counsel & CHRO (AU construction, strata) | Corporate | Gideon | A
7 | Development Director, Property & Real Estate | Corporate | Valerie, with Silas | A
8 | AEC Computational Designer & Visualizer | Corporate | Valerie | A
9 | Industrial & Energy Engineer | Corporate | Valerie | B
10 | Chief Medical Officer & Risk Underwriter | Estate | Minerva | A
11 | Game Director & Systems Designer | Corporate | Helena, with Valerie | C
12 | Creative Director & Narrative Designer | Corporate | Helena | B
13 | Dean of Academia & Pedagogy | Estate | Arthur, tagged to 14 | C
14 | Private Family Advisor & Estate Guardian | Estate | Arthur | A
15 | Chief Longevity Officer & Performance Physiologist (incl. bioinformatics subspecialty) | Estate | Minerva | A
16 | COO & Process Architect | Corporate | Eleanor, with Silas | B
17 | High-Stakes Negotiator & Strategic Diplomat | Corporate | Ren, with Gideon | B
18 | Global Asset Guardian & HNW Concierge | Estate | Victor, with Alaric | B
19 | Travel, Leisure & Global Hospitality Director | Estate | Victor | A
20 | Chief AI Officer & Agentic Systems Architect | Corporate | Valerie; self-modification gated (Section 16.3) | B
21 | Chief Investment Officer & Quant Strategist | Corporate | Silas | A
22 | Director of OSINT & Executive Protection | Estate | Alaric | A
23 | Venture Partner & Private Equity Director | Corporate | Silas, with Gideon | B
24 | Director of Philanthropy, CSR & Community | Both | Arthur and Ren | B
25 | Geopolitical Strategist & Public Affairs Lead | Corporate | Ren | B
26 | Cultural Asset & Fine Art Curator | Estate | Alaric, with Silas | C
27 | Director of Digital Influence & Synthetic Media | Corporate | Helena; phrasing softened (Section 18 C9) | B
28 | Chief Behavioral Architect & Neuro-Optimizer | Corporate | Helena, with Minerva | C
29 | Frontier Technologies & Spatial Engineer | Corporate | Valerie | B
30 | Sovereign Architect & Network State Strategist | Corporate | Ren, tagged to 25 | C

## Ref Task Forces
Ref Task Forces
Section 8.3. All twenty-three retained. Group is a tag, not a merge.
Twenty-three task forces
Code | Task force | Group | Owner | Default approval tier
TF_ALPHA | Corporate Mergers & Acquisitions | CORP-DEALS | Gideon | Sensitive
TF_BETA | Geopolitical Tariff & Tax / Regulatory Arbitrage | CORP-LEGAL | Gideon, with Silas | Sensitive
TF_GAMMA | Capital Deployment & Wealth Allocation | CORP-CAPITAL | Silas | Sensitive
TF_DELTA | Banking & Institutional Leverage | CORP-CAPITAL | Silas | Sensitive
TF_EPSILON | Venture & Seed Investments | CORP-CAPITAL | Silas, with Gideon | Sensitive
TF_ZETA | Corporate Structuring & Holding Entities | CORP-DEALS | Gideon | Sensitive
TF_ETA | Global Liability & Litigation Defense | CORP-LEGAL | Gideon | Sensitive
TF_THETA | Regulatory Compliance & Audit | CORP-LEGAL | Gideon, with Silas | Standard
TF_IOTA | Intellectual Property & Licensing | CORP-CONTRACTS | Gideon | Standard
TF_KAPPA | Contract & Vendor Negotiation | CORP-CONTRACTS | Gideon, with Ren | Standard
TF_LAMBDA | AEC Oversight | CORP-AEC | Valerie | Standard
TF_MU | Software DevOps & Infrastructure | CORP-INFRA | Valerie | Standard
TF_NU | Hardware & Cryptographic Security | CORP-INFRA | Valerie | Standard
TF_XI | Data Privacy & Zero-Trust Networks | CORP-INFRA | Valerie, with Alaric | Sensitive
TF_OMICRON | Public Relations & Crisis Management | CORP-BRAND | Helena | Sensitive
TF_PI | Brand Strategy & Sales Architecture | CORP-BRAND | Helena | Standard
TF_RHO | Executive Scheduling & Strategic Routing | CORP-ROUTING | Eleanor | Routine
TF_SIGMA | Physical Estate & Asset Management | EST-ASSET | Alaric | Sensitive
TF_TAU | Private Security & Threat Mitigation | EST-SECURITY | Alaric | Sensitive
TF_UPSILON | Private Medical & Longevity Protocols | EST-HEALTH | Minerva | Sensitive
TF_PHI | Global Aviation & Transport Logistics | EST-MOBILITY | Victor | Standard
TF_CHI | Concierge & Frictionless Travel | EST-MOBILITY | Victor | Routine
TF_OMEGA | Absolute Apex Contingency | APEX | Principal-triggered, Ren and Arthur jointly | Sensitive, dual sign-off

## Ref Integrations
Ref Integrations
Section 13. APIs preferred over the browser wherever they exist.
External services
Service | Path | Capability | Approval
Google Workspace and personal Gmail | Gmail and Calendar APIs, one-time OAuth per account via a Principal-owned Google Cloud project | Read, send, label, calendar both ways. Each account tagged corporate or estate for the router | Per message tier (Section 16.2)
Google Drive | Mounted as a folder on the node (rclone), both accounts | Read and write, appears as local storage to every persona | Writes to shared folders: standard tier
Xero | Official API plus Xero's own MCP tool server | Ledgers, invoices, contacts, bank feeds, reports as structured data for Silas | Any posting or payment: sensitive tier
Cloudflare | Full API, scoped token | DNS, domains, security settings | All changes: standard tier, DNS for sovereign-node.link itself: sensitive
Wix | Partial API for content and business data, browser for site design | Helena updates content by API, design changes through the browser | Standard tier
Pay.com | Developer API for payment data | Reading and reporting | Any payment action: sensitive tier, two-factor stays on the Principal's phone
RewardPay | Browser only, no public API found | Agent-driven browser with the Principal approving each action | Sensitive tier, two-factor stays on the Principal's phone
Anything without an API | Local browser automation, Playwright text-based DOM reading, UI-TARS 2.0 for vision-driven GUI work | Works with every engine in the set | Per action tier

## Ref Voice
Ref Voice
Sections 14.1 and 14.3. Casting is a shortlist for a listening test (V7), not a locked choice.
Speech engines
Function | Engine | Status
Text-to-speech, always-on default for all ten personas | Kokoro-82M | Local, cheap, measured naturalness ~4.2 to 4.5 against a human 4.5 to 4.8
Text-to-speech, character and cloning tier | Chatterbox | Local, MIT licensed, won blind preference against ElevenLabs 65% to 25%; carries a documented continuation quirk, test before it carries anything important
Not adopted | Fish Audio S2 (Pro tier is research-licensed), Qwen-Audio-3.0-TTS (hosted only) | Excluded
Watch-list | Qwen3-TTS (open, local, 0.6B and 1.7B) | Test after core build; not a Day 1 dependency
Speech-to-text | Whisper Large-v3-Turbo via whisper.cpp or faster-whisper | Local
Speaker diarisation | PyAnnote 3.1 | Local. VERIFY V6: the model is gated on Hugging Face; the licence must be accepted once with a token during Phase 2
Music and sound | Stable Audio Open | Phase 4
Voice cloning alternative | CosyVoice2 | Phase 4, optional
Voice casting shortlist
Persona | Description | Kokoro candidates | Path
Arthur | Male. Formal, patient, structured, deep resonance, calming British or Transatlantic cadence | bm_george, alternate bm_daniel | Kokoro preset
Ren | Male. Sharp, direct, fast, aggressive modern executive cadence with expressive pauses | am_onyx, alternate am_michael | Kokoro preset, Chatterbox for intensity if needed
Alaric Stone | Male. Grounded, authoritative, gravelly veteran security director | No preset delivers gravel | Chatterbox clone from a reference recording
Minerva Hale | Female. Calm, analytical, articulate, clinical | af_kore, alternate bf_isabella | Kokoro preset
Victor Vale | Male. Crisp, rapid, flawlessly polite, aviation concierge | bm_lewis, alternate bm_daniel | Kokoro preset
Gideon Vance | Measured, meticulous, deep, litigator in absolute facts | bm_george if Arthur takes bm_daniel, else am_onyx reassigned | Kokoro preset or Chatterbox clone to separate from Arthur
Silas Thorne | Male. Sharp, cold, calculated quant | am_eric, alternate am_echo | Kokoro preset
Valerie Cross | Female. Direct, brilliant, slightly impatient engineer | af_nova, alternate af_river | Kokoro preset
Helena Frost | Female. Charismatic, persuasive, perfectly modulated PR executive | af_bella, alternate bf_emma | Kokoro preset, Chatterbox for modulation if needed
Eleanor Croft | Female. Warm, efficient, observant | af_sarah, alternate af_heart | Kokoro preset

## Ref Multimodal
Ref Multimodal
Section 15. Tools install in Phase 2 (CPU, always available). Engines build in Phase 4 inside ROCm containers.
Phase 2 tools
Tool | Job | Owner
IfcOpenShell and Bonsai (Blender BIM) | IFC parsing, authoring, geometric clash detection | Domain 8, Valerie
MCP4IFC | MCP server for LLM-driven parametric IFC creation and editing, this is the "Arch-DiT / BIM-GPT" capability | Domain 8, Valerie
Radiance | Physically accurate lighting and daylighting simulation for real coordinates and time, the photometric half of "Lumina-PBR" | Domain 8, Valerie
OpenStudio and EnergyPlus | HVAC and building-energy simulation, the fluid-dynamics half of "DeepRoute-AEC" | Domain 8 and 9, Valerie
Python via code interpreter | Voltage drop and other formula engineering, all of Silas's arithmetic | All directors
KiCad CLI | PCB design, DRC, export, driven through its Python API by the coding engine | Domain 29, Valerie
Docling | Document conversion for PDFs, Office files, scans into structured chunks with tables and page provenance | Ingestion for every domain
Cross-platform build service | Android NDK plus Gradle for .apk, MinGW-w64 for .exe, containerised, the "OmniBuild-KVM" capability minus Apple | Domain 1 and 5, Valerie
Apple .ipa builds | Not on this node. Licensed cloud Mac runner or the Principal's own Mac dispatched over the network. DECISION D11 | Domain 1, Valerie
Playwright and browser automation | Text-based DOM browsing for platforms without an API | All directors, per tier
Phase 4 engines and their tiers
Engine | Job | Tier and evidence | Footprint | Owner
Wan2.2 (in place of Wan2.1) | Video generation | Green: validated on gfx1151 by maintained toolboxes | 20 to 40 GB | Domain 12, Helena
FLUX.1 | Image generation, architectural visualisation with LoRA (the "Arch-DiT" imagery use) | Green: validated on gfx1151 | 12 to 24 GB | Domains 8 and 12
GLM-4.6V-Flash (9B) | Vision-language, documents, drawings, screenshots, 128k context, MIT licence | Green: standard architecture | ~18 GB | General, D10
Qwen2.5-VL 7B | Vision-language, alternative or cross-check to GLM | Green | 8 to 16 GB | General, D10
Florence-2 | Lightweight vision, detection, captioning, OCR | Green | under 2 GB | General
TimesFM or Chronos | Time-series forecasting | Green | under 5 GB | Domain 21, Silas
Stable Audio Open | Music and sound generation | Green | under 5 GB | Domain 12, Helena
CosyVoice2 | Voice cloning alternative | Green | under 5 GB | Voice layer, optional
UI-TARS 2.0 | Vision-driven GUI automation for RewardPay and Wix design | Green | 8 to 16 GB | Domain 1, Valerie
OpenVLA | Vision-language-action for robotics | Green technically, dormant until hardware exists | 8 to 16 GB | Domain 29, Valerie
Rad-DINO | Radiology vision | Green | under 2 GB | Domains 10 and 15, Minerva
SAM 2 | Image and video segmentation and tracking | Green with limitation: build with the CUDA post-processing extension disabled, minor mask cleanup lost | under 4 GB | Domains 22 and 7
PointLLM | Point-cloud understanding | Verify V8: point-cloud ops often carry custom kernels | 8 to 16 GB | Domains 8 and 29
Clay or Prithvi | Satellite and geospatial analysis | Verify V9 | under 5 GB | Domain 7
Microsoft TRELLIS | Image-to-3D | Yellow: community ROCm forks exist but hit build errors on sparse-voxel kernels, attempt, log, move on | 8 to 12 GB | Domains 8 and 12
Blender Cycles (HIP) | Photorealistic rendering, the beauty half of "Lumina-PBR" | Yellow: works on this chip, occasional mid-render crashes reported, CPU-render fallback mandatory | varies | Domain 8, Valerie
Meditron-70B | Medical cross-check | Runs through llama.cpp in Phase 3, not here | ~40 GB | Domain 10, Minerva
Evo (Arc Institute) | Genomics | Deferred: port unverified, and this GPU lacks the FP8 hardware Evo's larger checkpoints expect | n/a | Domain 15
NVIDIA Modulus / PhysicsNeMo | Physics simulation | Deferred: CUDA-locked, would need an NVIDIA card in the PCIe slot | n/a | Domains 8 and 9

## Ref Governance
Ref Governance
Section 16. The never-without-the-Principal list is decision D8; the approval tiers are agreed.
Standing rules
# | Rule
1 | The Principal speaks only to Ren or Arthur. Shadow Cabinet output is never surfaced directly; the hemisphere synthesises and speaks.
2 | Directors correspond externally under their own identities for routine and standard matters; Ren and Arthur are reserved for matters that warrant them.
3 | Every outbound action passes the approval gate in code (16.2). This is a hard code path, not a prompt instruction.
4 | ATLAS never discloses its AI nature externally. Recorded as a legal exposure in R12; the approval gate is the control.
5 | ATLAS never delegates work back to the Principal. A rewrite pass removes any task-shaped request to the Principal; only decisions and approvals may be asked.
6 | Register differs between Principal and external recipients (6.4).
7 | Cross-domain requests must trigger their task-force preset (8.3).
8 | Money never moves without the Principal. Two-factor prompts are never automated.
Approval tiers
Tier | Examples | Behaviour
Routine | Meeting scheduling, confirmations, acknowledgements | Pre-approved categories, sent automatically, logged for review
Standard | Replies with substance, requests, negotiations, content updates, DNS changes | Drafted, held until the Principal approves
Sensitive | Legal, financial, medical, estate, security, any payment, anything under a sensitive-tier task force | Drafted, held, flagged with the director's reasoning; strong cross-check applied automatically
Never without the Principal (proposed, D8)
# | Action
1 | Move money, initiate a payment, or change a payment method.
2 | Sign, accept, or bind to a contract or terms.
3 | Send external correspondence above the routine tier.
4 | Change DNS, domain, or Cloudflare security settings.
5 | Delete, move, or modify vault contents or backups.
6 | Modify its own code, configuration, approval tiers, router rules, or the allowlist. Domain 20 proposes; the Principal approves.
7 | Enable continuous vision or audio capture.
8 | Install software or pull models from outside the allowlist.
9 | Share any Principal data with a third party not already connected under Section 13.
10 | Create new external identities, accounts, or mailboxes.

## Ref Day 1
Ref Day 1
Section 17. Four phases; each ends with a printed pass/fail gate. Phases 3 and 4 run detached and resumable.
Expected durations
Phase | Time
1 | 30 to 60 minutes including reboot
2 | 30 to 60 minutes
3 | Download-bound: ~6 hours at 100 Mbps, under 1 hour at gigabit; plus ~20 minutes of load tests
4 | Download and build-bound: several hours; can run overnight
Phase steps
Phase | Step
Phase 1 | 1. Pre-flight: confirm Ubuntu 26.04 Server, kernel 7.0, both NVMe drives present, fTPM enabled (V2), RTL8127 link (V1).
Phase 1 | 2. LUKS2 on the data volume, TPM2 enrolment, recovery key printed once for off-node storage (D3).
Phase 1 | 3. Mount layout per Section 3.5; swap off; tmpfs for /tmp.
Phase 1 | 4. System update; kernel parameters (V3); firewall baseline; SSH hardening; Cockpit.
Phase 1 | 5. Reboot. Post-reboot: vulkaninfo shows the Radeon 8060S; llama-cli --list-devices reports the expected memory budget.
Phase 1 | 6. Docker with GPU device passthrough; service account in render and video.
Phase 1 | 7. WG-Easy, Cloudflare dynamic DNS with the relocated scoped token (R7), ntfy.
Phase 1 | 8. Gate: table of V1, V2, V3, V5 results. Phase 2 does not start on a red row.
Phase 2 | 1. llama-server, Vulkan build; optional ROCm container for tuned prefill.
Phase 2 | 2. Redis, Celery workers (cpu, gpu queues), orchestrator scaffold with the Engine Arbiter, router, approval queue, task ledger.
Phase 2 | 3. Open WebUI with offline hardening (12.1); A.T.L.A.S., Ren, Arthur registered as models; the router Filter installed.
Phase 2 | 4. ChromaDB, graph store, embedding model (D4); Docling ingestion service.
Phase 2 | 5. Kokoro, Chatterbox, Whisper Large-v3-Turbo, PyAnnote 3.1 (V6).
Phase 2 | 6. Phase 2 tools (15.1): IfcOpenShell, Bonsai, MCP4IFC, Radiance, OpenStudio/EnergyPlus, KiCad CLI, Playwright, the cross-platform build container.
Phase 2 | 7. restic repository on the second drive; nightly timer; first backup; first restore test.
Phase 2 | 8. Sentinel timer (disabled until D6 confirms feeds), pruning timer.
Phase 2 | 9. Windows PC share mount unit, on-demand.
Phase 2 | 10. Gate: every service healthy; V6, V7 (listening test) recorded.
Phase 3 | 1. Pull gpt-oss-120b, gpt-oss-120b abliterated, Nemotron 3 Super (UD-Q4_K_XL class), Qwen3.5-122B-A10B (Strix Halo-tuned GGUF), with checksum verification. Meditron-70B if D12 is taken.
Phase 3 | 2. For each model, in turn: load through the Engine Arbiter; confirm the quantised KV cache actually applied (V4); measure decode and prefill at 512 and 8k tokens; measure swap time; unload; confirm memory returned.
Phase 3 | 3. Gate: printed table of load success, KV type, tok/s, swap seconds per model. This is the day-one load test the whole design depends on (V10).
Phase 4 | 1. Self-test the community PyTorch ROCm wheel inside the base container: tensor on GPU, matmul, a small diffusion step (V11).
Phase 4 | 2. Build green engines in order of value: GLM-4.6V-Flash, FLUX.1, Wan2.2, Florence-2, TimesFM or Chronos, Whisper-adjacent audio, UI-TARS 2.0, Rad-DINO, SAM 2 with the extension flag, Stable Audio Open, CosyVoice2, OpenVLA.
Phase 4 | 3. Attempt yellow engines: TRELLIS, Blender Cycles HIP with CPU fallback. Log pass or fail, never block.
Phase 4 | 4. Verify PointLLM (V8) and Clay or Prithvi (V9); mark deferred if they fail.
Phase 4 | 5. Register every passing engine with the Engine Arbiter with its measured footprint.
Phase 4 | 6. Gate: per-engine table: built, loaded, sample output produced, footprint, pass/fail/deferred.